## Bug Triage
jira_key | project | summary | issue_type | jira_status | jira_url | reporter | assignee | created_date | updated_date | environment | affected_version | fix_version | labels | components | existing_jira_severity | existing_jira_priority | defect_disposition | recommended_severity | recommended_priority | category | suspected_layer | blast_radius | reproducibility | workaround_available | regression | technical_impact | business_impact | triage_rationale | severity_priority_explanation | likely_root_cause | missing_information | assumptions | confidence | recommended_action | triage_status | processing_error
EA-40 | Enterprise Application | Cross-browser QA: editor preview broken in Safari (layout shift) | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-40 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:48.410+05:30 | 2026-09-01T23:36:53.878+05:30 |  |  |  | bug,cross-browser,enterprise-app,previews,qa |  |  | Medium | Valid Defect | S3 - Minor | P2 - Next Sprint | UI/UX and Layout | Frontend | Specific segment (Safari desktop) | Always | Yes | No | Visual/layout inconsistency in preview; low | Moderate for QA and previews; may affect shipping confidence | Layout shift observed only in Safari previews; reproduction steps provided. Not a data or security issue; impacts developer/QA experience. | Severity is minor (visual), but priority set to P2 to schedule fix in upcoming sprint for cross-browser parity. | CSS rendering differences or browser-specific layout handling in preview component | Browser version details; screenshot or recording; console logs | Issue limited to Safari desktop; other browsers unaffected | Medium | Plan for Next Sprint | Triaged
EA-39 | Enterprise Application | Session recordings stop after 30 seconds on long pages | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-39 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:47.504+05:30 | 2026-09-01T23:36:53.302+05:30 |  |  |  | bug,enterprise-app,insights,recordings |  |  | Medium | Valid Defect | S2 - Major | P1 - Current Sprint | API and Integration | Backend | Many users on heavy DOM pages | Always | No | No | Missing portions of user sessions; impacts analytics accuracy | High for product analytics and troubleshooting; could miss critical user issues | Playback truncates at ~30s on heavy DOM pages; reproduction steps provided. Likely backend ingestion or buffer limit. | Because analytics data is incomplete and loses critical session context, severity is S2 and priority elevated to P1 for timely fix. | Recording ingestion buffer or chunking issue on heavy DOM pages causing early termination | Server logs; retention config; sample recording; environment details | Issue occurs on pages with heavy DOM only | Medium | Fix in Current Sprint | Triaged
EA-38 | Enterprise Application | Heatmaps fail to render for pages behind login | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-38 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:46.698+05:30 | 2026-09-01T23:36:53.116+05:30 |  |  |  | bug,enterprise-app,heatmaps,insights |  |  | High | Valid Defect | S2 - Major | P1 - Current Sprint | API and Integration | API or Integration | Many users using authenticated pages | Always | No | No | Insights missing for auth pages; reduces product observability | High for customers tracking authenticated funnels | Heatmaps show blank canvas for auth-walled pages; likely token/cookie handling in tracking pipeline. | Data capture failing for core analytics makes this S2 and P1 to avoid blind spots in customer analytics. | Tracking script not including auth tokens or server-side filtering of auth pages | Auth flow details; tracking config; sample protected page URL | Issue is specific to authenticated pages | Medium | Fix in Current Sprint | Triaged
EA-37 | Enterprise Application | Visual editor changes not reflected in live preview | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-37 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:45.671+05:30 | 2026-09-01T23:36:52.489+05:30 |  |  |  | bug,editor,enterprise-app,preview,visual-editor |  |  | High | Valid Defect | S2 - Major | P1 - Current Sprint | UI/UX and Layout | Frontend | Many users using visual editor | Always | Workaround (hard refresh) | No | Editor-preview pipeline inconsistent; editing workflow degraded | High for conversion-focused users who rely on immediate previews | Changes require hard refresh to appear; reproduction steps and acceptance criteria indicate developer/user impact. | Immediacy of editing workflow is critical; set S2 and high priority to restore NFRs. | Preview rendering cache or incremental build pipeline not invalidating updated assets | Browser/dev console logs; frequency of occurrence; sample payloads | Issue affects visual editor only | Medium | Fix in Current Sprint | Triaged
EA-36 | Enterprise Application | SmartStats confidence metric incorrect for small sample sizes | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-36 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:44.729+05:30 | 2026-09-01T23:36:52.306+05:30 |  |  |  | bug,enterprise-app,smartstats,statistics |  |  | High | Valid Defect | S2 - Major | P1 - Current Sprint | Data and Calculation | Backend | Many experiments (small-sample scenarios) | Always | No | No | Incorrect statistical output could mislead decisions | High for customers relying on SmartStats conclusions | High confidence outputs on low samples can cause incorrect product decisions; statistical fix required. | Data integrity issue in analytics considered major (S2); priority P1 to avoid misleading customers. | Bayesian engine or prior handling not accounting for low sample sizes; missing guardrails | Exact confidence calculation examples; sample sizes used; logs of algorithm output | Occurs when sample sizes below threshold | Medium | Fix in Current Sprint | Triaged
EA-35 | Enterprise Application | A/B test variations not distributed evenly under high traffic | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-35 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:43.828+05:30 | 2026-09-01T23:36:52.068+05:30 |  |  |  | ab-testing,bug,enterprise-app,testing |  |  | High | Valid Defect | S2 - Major | P1 - Current Sprint | API and Integration | Backend | Many experiments under load | Always under load | No | No | Traffic split skew affects experiment validity | High for A/B testing customers; could invalidate results | Distribution skew under load indicates deterministic or race condition in allocation; needs immediate attention. | Statistical integrity is critical; set S2 and P1 to avoid false conclusions in tests. | Load-induced hashing/partitioning bug or concurrency in allocation service | Load test logs; sampling distribution data; environment specifics | Issue manifests under high throughput | Medium | Fix in Current Sprint | Triaged
EA-34 | Enterprise Application | Duplicate registration email returns 200 instead of a conflict error | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-34 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:42.950+05:30 | 2026-09-01T23:36:51.594+05:30 |  |  |  | api,bug,enterprise-app,registration,signup |  |  | Medium | Valid Defect | S1 - Critical | P1 - Current Sprint | API and Integration | Backend | Potentially many registrations | Always | No | No | Duplicate accounts possible; data integrity risk | High risk of account duplication and incorrect user state | API returns 200 on duplicate email, which can create duplicate accounts; must be treated as critical for data integrity. | Data-corruption potential elevates severity to S1 and priority to P1 for immediate fix. | User creation endpoint not validating uniqueness or returning wrong status code | API logs; request/response examples; DB uniqueness constraints | Duplicate account actually created rather than ignored | Medium | Fix in Current Sprint | Triaged
EA-33 | Enterprise Application | proxyToken and playerToken missing from login success response | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-33 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:42.123+05:30 | 2026-09-01T23:36:51.428+05:30 |  |  |  | api,bug,enterprise-app,login,token |  |  | High | Valid Defect | S1 - Critical | P1 - Current Sprint | API and Integration | Backend | All login clients dependent on tokens | Always | No | No | Clients fail due to missing tokens; authentication broken | Critical — blocks client integrations and login flows | Login response missing required fields per contract; immediate fix required to restore clients. | Authentication contract breach is critical (S1) and requires P1 priority to restore integration compatibility. | Backend auth service failing to include tokens in response or serialization bug | Server logs; example response payload; affected client versions | All clients rely on these tokens | High | Hotfix Immediately | Triaged
EA-32 | Enterprise Application | Session cookie not honored on subsequent authenticated API requests | Bug | To Do | https://shivanandreure90.atlassian.net/browse/EA-32 | SHIVANAND REURE | SHIVANAND REURE | 2026-09-01T23:36:41.239+05:30 | 2026-09-01T23:36:51.256+05:30 |  |  |  | bug,cookie,enterprise-app,login,session |  |  | High | Valid Defect | S1 - Critical | P1 - Current Sprint | API and Integration | Backend | All authenticated sessions | Always | No | No | Broken session handling prevents authenticated actions | Critical for login flows and user sessions | Set-Cookie not honored causing 401 on next request; affects all authenticated flows. | Authentication/session failure is critical (S1) and needs P1 priority for immediate resolution. | Cookie attributes (Domain/Path/SameSite) misconfigured or missing secure flags | Request/response headers; cookie attributes; client environment | Set-Cookie is sent but not returned by clients | Medium | Hotfix Immediately | Triaged

## Run Summary
total_issues_retrieved | total_issues_triaged | total_errors | retrieval_complete | retrieval_notes
4 | 4 | 0 | TRUE | Sample workbook — replace these values with the current Jira run summary.

## Field Guide
# | Column | Purpose
1 | jira_key | Unique Jira issue key; use this as the append-or-update match column.
2 | project | Jira project name or key.
3 | summary | Short issue title.
4 | issue_type | Bug, Story, Task, Epic, and so on.
5 | jira_status | Current Jira workflow status.
6 | jira_url | Direct URL to the Jira issue.
7 | reporter | Issue reporter.
8 | assignee | Current assignee or Unassigned.
9 | created_date | Jira creation timestamp.
10 | updated_date | Most recent Jira update timestamp.
11 | environment | Production, staging, QA, development, or Not Provided.
12 | affected_version | Version where the issue occurs.
13 | fix_version | Planned or released fix version.
14 | labels | Comma-separated Jira labels.
15 | components | Comma-separated Jira components.
16 | existing_jira_severity | Severity already recorded in Jira.
17 | existing_jira_priority | Priority already recorded in Jira.
18 | defect_disposition | Triage verdict, such as Valid Defect or Test Automation Issue.
19 | recommended_severity | Technical impact: S0 through S4.
20 | recommended_priority | Business urgency: P0 through P4.
21 | category | Closest single root-cause category.
22 | suspected_layer | Most likely affected system layer.
23 | blast_radius | Estimated affected population without inventing percentages.
24 | reproducibility | Always, Intermittent, Unable to Reproduce, and so on.
25 | workaround_available | Yes, No, or Unknown.
26 | regression | Whether evidence shows it worked before.
27 | technical_impact | Concise technical consequence.
28 | business_impact | Concise user, revenue, compliance, or operational consequence.
29 | triage_rationale | Evidence-based explanation of the verdict.
30 | severity_priority_explanation | Why severity and priority align or differ.
31 | likely_root_cause | Evidence-based hypothesis; use Unknown when unsupported.
32 | missing_information | Semicolon-separated facts needed for stronger triage.
33 | assumptions | Semicolon-separated assumptions used in the verdict.
34 | confidence | High, Medium, or Low.
35 | recommended_action | The next operational action.
36 | triage_status | Triaged, Pending Review, or Processing Error.
37 | processing_error | Per-issue processing failure; blank for successful triage.

## Lists
Defect Disposition | Severity | Priority | Category | Suspected Layer | Blast Radius | Reproducibility | Yes / No / Unknown | Confidence | Recommended Action | Triage Status
Valid Defect | S0 - Blocker | P0 - Immediate | Functional Logic | Frontend | All users | Always | Yes | High | Hotfix Immediately | Triaged
Likely Defect | S1 - Critical | P1 - Current Sprint | Data and Calculation | Backend | Many users | Intermittent | No | Medium | Fix in Current Sprint | Processing Error
Needs More Information | S2 - Major | P2 - Next Sprint | UI/UX and Layout | API or Integration | Specific user segment | Unable to Reproduce | Unknown | Low | Plan for Next Sprint | Pending Review
Expected Behaviour | S3 - Minor | P3 - Opportunistic | Performance | Database or Data | One account | Not Provided |  |  | Keep in Backlog
Duplicate | S4 - Trivial | P4 - Backlog | Security | Infrastructure or Deployment | Internal users only | Not Applicable |  |  | Request More Information
Test Automation Issue |  |  | API and Integration | Authentication or Security | Unknown |  |  |  | Reproduce and Investigate
Environment or Configuration Issue |  |  | Compatibility | Test Automation |  |  |  |  | Route to Security Team
Test Data Issue |  |  | Configuration and Deployment | Test Data |  |  |  |  | Route to Development Team
Enhancement Request |  |  | Regression | Third-Party Service |  |  |  |  | Route to Test Automation Team
Not Applicable |  |  | Usability and Content | Cross-Layer |  |  |  |  | Route to DevOps Team
Unable to Determine |  |  | Test Automation | Unable to Determine |  |  |  |  | Route to Product Team
|  |  | Test Data | Not Applicable |  |  |  |  | Close as Expected Behaviour
|  |  | Not Applicable | [5 empty] | Close as Duplicate
|  |  | Unable to Determine | [5 empty] | Convert to Enhancement
No Triage Required